2012 Stanford SOE UGVR Program Timeline

| Date | Activity |
| --- | --- |
| Nov 4 | SU SOE send out UGVR program announcement to SU faculty |
| Nov 14 | Get interest indication from SU faculty |
| Dec 9 | Interested SU SOE faculty members submit position descriptions and required skills/background |
| Dec 16 | Partner Chinese Universities receive SU position descriptions and make it known to their students |
| Feb 28 | Partner Chinese Universities collect applications and pre-select candidates. Each school chooses 3 students for each position and send application materials to SU faculty members |
| March 15 | SU faculty members review application materials and make final decisions |
| March 25 | SU notifies the selected students and get acceptance confirmation. Students submit application forms and passport copies to SU |
| April 1 | SU submits paperwork to registrar and get approval, obtain student IDs, SEVIS Form DS-1029, etc. |
| Late April | UGVR students receive official invitation letters and DS-1029 forms |
| April/ May | UGVR students go for visa application and obtain US visas |
| May | SU helps students to do housing application and make travel arrangement |
| June 25 – Aug 31 | UGVR students conduct summer research at Stanford |